## Nov, 2021
ACTION POINT REGISTER
ACTION POINT REGISTER
Total action points
Site/Vessel | ENL SUPERIOR | [9 empty] | Closed action points
Updated | 2021-11-03 |  |  | 0 | [6 empty] | Percentage closed
| Class Dry-Dock Survey Close out Actions | Responsibility for Close Out |  |  | Dates
S/N | Description of work | CO. | Person / Supdt | Priority | Opened | Target Set | Status (CE/Capt) | Projected Budgeted Amount | DPA Comment | Requisition No | Captain and Chief engineer Comment | Marine Consultant | Procurement Comments
A | BV Surveyors 1st attendance observations
1 | Port and Starboard ballast tanks corroded, require chipping and painting, before carruing out thickness measurement. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Closed | N/A | This observation was closed out at the dock yard with the chipping and painting of both ballast tanks and conducting of Utrasonic tests in 60 point of the ballast tanks.
2 | Replacement of Port and starboard fire flap seal. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 34500 | To be handled by deck crew, requisition to be raised for purchase of seals and adhesive to replace seal
3 | Welding repair of deck vents | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 107000 | To be worked on with the fender installation fund has been released.
B | BV Surveyors 2nd attendance observations
1 | Provide manual for oily water seperator | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Closed | N/A | Chief Engr. has provided for sighting. | ???
2 | Proved running hours for main and auxiliary engines and megga test reports to surveyor for sighting. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Closed | N/A | Chief Engr. has provided for sighting.
C | BV Surveyors 3rd attendance observations
1 | Provide dry dock report, Oil cooler, Heat exchanger and auxiliary electric motors work done reports. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Closed | N/A | Dry dock report sent to BV surveyor by DPA. Other reports to be sent on 04.11.21.
2 | Auxiliary engine sea water strainer boxes to be re-fabricated and intalled | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 200000 | Cost for fabricating port and starboard strainer boxes obtained awaiting approval and release of fund.
3 | Replacement of sea water pump for main winch | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | TBA | Requisition to be raised for procurement to handle
4 | Replace corroded auxiliary engines sea water pipes for port and starboard lines | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 110000 | To be handled by welder after installation of fenders, installation of Triumph 2 winch and repair of deck vents. | ???
5 | Replace main winch hydraulic lines with new pipes. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 46800 | To be handled by welder after installation of fenders, installation of Triumph 2 winch and repair of deck vents.
6 | Repair defective fresh water cargo pump and provide repair report. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 18000 | Requisition and cost of repair to be provided by Chief Engineer Akpotu
7 | Service main engines oil cooler and heat exchangers and provide work don report. | Elshcon | DPA, C/E/Engr. Berembo, ENL Superior crew, Niger-Dock | High | 2021-10-21 | 2021-11-14 | Open | 16500 | Requisition and cost of repair to be provided by Chief Engineer Akpotu | ???