## General
Emergency Restoration of Flowlines for Wells 4 S (5.35Km) in Cawthone Channel 3
S/N | Description of Activity | Qt'y | UoM | Dur. | Rate | Amount |  | Quoted Cost | Actual Execution cost
1 | Major Procured items |  |  |  |  | 0 |  | 186500000 | 155760000
2 | Services |  |  |  |  | 0 |  | 27500000 | 19800000
3 | Accommodation |  |  |  |  | 0 |  | 27220000 | 18036000
4 | Marine Equipment |  |  |  |  | 0 |  | 62900000 | 48420000
5 | Other Expenses |  |  |  |  | 0 |  | 68160000 | 31480000
6 | Safety Requirement |  |  |  |  | 0 |  | 2557000 | 1289300
7 | Welding (Ancillary Material.) |  |  |  |  | 0 |  | 12626500 | 2526800
8 | Personnel |  |  |  |  | 0 |  | 36410000 | 34955000
9 | Security |  |  |  |  | 0 |  | 67640000 | 62950000
10 | Extra cost for Equipt./Skilled | [6 empty] | 15000000 | 15000000
[7 empty] | GRAND TOTAL | 491513500 | 375217100
[9 empty] | 116296400 | 23.6609
Other Details
[6 empty] | Total cost less Procured items |  | 305013500
[6 empty] | Mob/Demob costs (20% + 15%) |  | 106754725 | 491513500
[6 empty] | Balance 65% |  | 198258775
6007841.6667
[7 empty] | Mob cost 20% of Total cost less procured items | DeMob cost 15% of Total cost less procured items
[7 empty] | 61002700 | 45752025
[7 empty] | 45902476 | 34426857

## Major Procure items
Emergency Restoration of Flowlines for Wells 45 (5.35Km) in Cawthone Chalnnel 3
S/N | Description of Activity | Qt'y | UoM | Dur. | Rate | Amount | Remarks | Actual
1 | Pipeline X56 PE coated 4" OD | 600 | Joints |  | 300000 | 180000000 |  | 150000000
2 | Elbow X56 PE coated | 20 | Ea |  | 25000 | 500000 |  | 360000
3 | Canusa Shrink Sleeve 4" | 600 | Ea |  | 10000 | 6000000 |  | 5400000
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
[6 empty] | 186500000 |  | 155760000

## Service
Emergency Restoration of Flowlines for Wells 45 (5.35Km) in Cawthone Chalnnel 3
S/N | Description of Activity | Qt'y | UoM | Dur. | Rate | Amount | Remarks | Actual
1 | NDT (X-Ray) |  |  |  |  | 6000000 |  | 5200000
2 | Pressure Testing/Hydrotesting |  |  |  |  | 5500000 |  | 3800000
3 | Surveying |  |  |  |  | 8500000 | Re-open Boundary, Peg/Set out the line Bush clearing Supervise excavation Pre-sounding of River-Crossing Post sounding of River-Crossing As-Built documentation | 6500000
4 | Cathodic Protection (CP) |  |  |  |  | 7500000 |  | 4300000
|  |  |  | TOTAL |  | 27500000 | 0 | 19800000

## Marine Equipment
S/N | Description of Activity | Qt'y | UoM | Dur. | Rate | Amount | Remarks | Actual
1 | Swamp Buggy | 1 | Ea | 50 | 300000 | 15000000 |  | 14000000
2 | Barge 1 | 1 | Ea | 40 | 150000 | 6000000 | 1 - to convey Swamp Buggy 1 - to convey Pipes etc | 5000000
| Barge 2 | 1 | EA | 5 | 150000 | 750000 | Drop off Pipe and leave | 500000
3 | Tug Boat 1 | 1 | Ea | 5 | 150000 | 750000 | 1 - to convey 1 nos. of Swamp Buggy on a barge 1 - to convey Pipes 1 - to push the Laybarge | 5000000
4 | Tug Boat 2 | 2 | Ea | 40 | 150000 | 12000000 |  | 500000
4 | Laybarge and all its appurtenances | 1 | Ea | 50 | 260000 | 13000000 |  | 6600000
5 | Covered CREW BOAT for team | 2 | Ea | 50 | 150000 | 15000000 | For the Crew - 1Nos. For Clients - 1Nos. | 16500000
6 | Empty Sealed Iron Drums for River Crossing | 40 | Ea | 1 | 10000 | 400000 |  | 320000
12 | EQUIPMENT LOSS COST |  | Ea |  |  | 0
[5 empty] | Total | 62900000 | 0 | 48420000
Note on B13: Raph: This is the cost for the equipment slot for the community

## Other Expenses Plus Fuel
﻿S/N | DESCRIPTION | QTY | DUR. | UoM | UNIT COST | TOTAL | Remarks | Actual
1 | CREW BOAT | 240 | 50 | LITRES | 1500 | 18000000 | 6 CREW BOATS @40 LITRES EACH | 14400000
2 | SWAMP BUGGY DIESEL | 150 | 50 | DRUMS | 1500 | 11250000 |  | 6600000
3 | Generator FUEL | 50 | 50 | LITRES | 1500 | 3750000 |  | 1080000
4 | Self Weld | 50 | 30 | LITRES | 1500 | 2250000 |  | 540000
5 | TUG BOATS | 10000 | 2 | LITRES | 1500 | 30000000 | Lumpsum for all the Tug boat movt. | 6000000
6 | MOBILE TOILET | 2 | 60 | DAYS | 15000 | 0 |  | 0
7 | MANUAL EXCAVATION | 2 | 8 | PERSONS | 10000 | 160000 |  | 160000 | after lay/weld
8 | STATION GUARDS | 4 | 50 | DAYS | 10000 | 2000000 |  | 2000000
9 | MISCELLENOUS |  |  |  | LUMPSUM | 500000 |  | 500000
10 | SITE WATER | 90 | 1 | CARTONS | 2200 | 250000 | 90 cartons of AquaDana water @N2,500/carton Plus 30 bags of pure water. | 200000
[5 empty] | TOTAL | 68160000 |  | 31480000
0

## Safety requirments
S/N | DESCRIPTION | QTY | UoM | UNIT COST | TOTAL | Actual
1 | WORK VEST | 50 | Ea | 20000 | 1000000 | 300000
2 | WELDERS / FITTERS PPE MONEY | 4 | Ea | 50000 | 200000 | 200000
3 | RAIN BOOTS | 37 | Ea | 15000 | 555000 | 250000
4 | HARD HAT | 37 | Ea | 2500 | 92500 | 125000
5 | COVERALL | 37 | Ea | 10000 | 370000 | 175000
6 | RAIN COATS | 37 | Ea | 2000 | 74000 | 125000
7 | HAND GLOVES (DOTTED) | 2 | DOZEN | 4000 | 8000 | 16800
8 | HANDGLOVES (HARD) | 2 | DOZEN | 10000 | 20000 | 30000
10 | EYE GOOGLES | 50 | pcs | 2000 | 100000 | 15000
11 | WELDING MASK | 4 | pcs | 30000 | 120000 | 20000
12 | FACE SHIELD | 3 | Ea | 2500 | 7500 | 4500
13 | EAR PLUG | 1 | PACK | 10000 | 10000 | 3000
15 | FIRST AID BOX | 1 | BOX | LS | 300000 | 25000
[5 empty] | 2557000 | 1289300
1261300

## Welding (Ancillary Material.)
﻿S/N | DESCRIPTION | QTY | Actual Qty | UoM | UNIT COST | TOTAL | Actual
1 | 9" CUTTING DISC (FLEXOVITE) | 30 | 30 | Pcs. | 10000 | 300000 | 120000
2 | 9" CUTTING DISC (POWER MASTER) | 30 | 20 | Pcs. | 10000 | 300000 | 100000
3 | 4.5" CUTTING DISC | 60 |  | Pcs. | 7000 | 420000 | 225000
4 | 9" GRINDING DISC | 10 |  | Pcs. | 10000 | 100000 | 300000
5 | CHAIN BLOCK | 1 |  | Pcs. | 50000 | 50000 | 65000
6 | POWER BRUSH | 8 |  | EA | 10000 | 80000 | 40000
7 | FLEET ELECTRODE (6010) 2.5MM | 11 |  | Tin | 400000 | 4400000
9 | SHIELD ARC ELECTRODE (7010) 3.2MM | 13 |  | Tin | 400000 | 5200000
11 | CAUTION TAPE | 2 | 1 | ROLL | 5000 | 10000 | 5000
12 | MATCHETS | 4 | 1 | EA | 3000 | 12000 | 3000
14 | 1’ MARINE ROPE | 1 | 1 | ROLL | 35000 | 35000 | 75000
17 | BERGER PAINT (GREEN) | 1 |  | TIN | 25000 | 25000 | 18000
18 | BERGER PAINT (BLACK) | 1 |  | TIN | 25000 | 25000 | 18000
19 | BERGER PAINT (YELLOW) | 1 |  | TIN | 25000 | 25000 | 18000
20 | SAND PAPER | 1 |  | ROLL | 10000 | 10000 | 5000
21 | FIRE EXTINQUISHER | 1 |  | UNIT | 5000 | 5000 | 48000
23 | PLAIN GLASS | 5 |  | SET | 100 | 500 | 5000
26 | RAG | 1 |  | BAG | 5000 | 5000 | 10000
27 | DETERGENT OMO | 1 |  | BAG | 5000 | 5000 | 20000
28 | PROPANE GAS (12.5 KG) | 10 |  | Bottle | 20000 | 200000 | 125000
29 | PROPANE TOUCH/HOSE | 4 |  | SET | 20000
30 | OXYGEN | 10 | 20 | Bottle | 8000 | 80000 | 150000
32 | 10MM PLATE SHEET | 2 | 2 | SHEET | 80000 | 160000 | 540000
33 | 32MM STUD BOLT/ NUT | 10 |  | Pcs. | 1200 | 12000 | 25000
31 | 36MM STUD BOLT / NUT | 10 |  | Pcs. | 1500 | 15000 | 25000
32 | 46MM STUD BOLT / NUT | 10 |  | Pcs. | 2000 | 20000 | 25000
33 | HSE BOARD | 1 |  | EA | 15000 | 15000 | 15000
34 | NOTICE BOARD | 1 |  | EA | 15000 | 15000 | 15000
35 | 2 - WAY -RADIO | 4 | 3 | EA | 50000 | 200000 | 20000
36 | WELDERS UMBRELLA | 1 |  | UNIT | 10000 | 10000 | 20000
37 | WASTE BASKET | 3 | 2 | Pcs. | 5000 | 15000 | 32000
38 | BLACK WASTE BAG | 2 | 1 | DOZEN | 750 | 1500 | 5000
39 | SPARK LIGHTER | 5 |  |  | 1500 | 7500 | 3000
40 | COPPER HAMMER (3KG) | 3 | 2 |  | 30000 | 90000 | 30000
41 | PIPE MARKER | 6 | 3 |  | 1500 | 9000 | 2400
42 | GRINDING MACHINE (9’’ ) | 3 | 2 |  | 50000 | 150000 | 150000
43 | GRINDING MACHINE (4.5’’) | 2 | 1 |  | 25000 | 50000 | 45000
44 | EXTENSION CABLE | 2 | 2 |  | 50000 | 100000 | 36000
45 | HAND FILE | 2 | 2 |  | 1500 | 3000 | 2400
46 | ELECTRODE QUIVER | 2 | 1 |  | 30000 | 60000 | 3000
47 | MASKING TAPE | 10 | 5 |  | 1500 | 15000 | 5000
48 | INSULATION TAPE | 20 |  |  | 2500 | 50000 | 12500
50 | OXY/ACETY CUTTING-SET | 1 |  |  | 150000 | 150000 | 100000
51 | 4’’CLAMP | 1 |  |  | 55000 | 55000 | 1500
51 | 36’’FLOGGING SPANNER | 2 | 2 |  | 18000 | 36000 | 20000 | 2000 | 9 | 2 | 36000
52 | 41’’FLOGGING SPANNERS | 2 | 2 |  | 25000 | 50000 | 24000
53 | 42’’FLOGGING SPANNERS | 2 | 2 |  | 25000 | 50000 | 20000
54 | LOW HYDROGEN G10 ROYAL ARC |  | 1 |  | 55000
|  | SUB-TOTAL: |  |  |  | 12626500 | 2526800

## Personnel
SITE PERSONNEL SALARIES
S/N | DESCRIPTION | QTY | UNIT COST | DURATION (DAY) | QUOTED TOTAL COST | Actual | Remarks
1 | PROJECT ENGR | 1 | 25000 | 55 | 1375000 | 0 | ENL Staff
2 | HSE OFFICER | 1 | 15000 | 55 | 825000 | 0 | ENL Staff
3 | NDT PERSONNEL | 1 | 15000 | 55 | 825000 | 0 | Actual cost is @7,500 per day
4 | TALLY CLERK | 1 | 15000 | 40 | 600000 | 562500 | Actual cost is @7,500 per day
5 | SITE NURSE | 1 | 15000 | 55 | 825000 | 450000 | Actual cost is @7,500 per day
6 | WELDERS | 600 | 20000 | NA | 12000000 | 12000000 | @N5000 per inch
7 | FITTER | 600 | 20000 | NA | 12000000 | 12000000 | @N5000 per inch
8 | GRINDERS | 4 | 13000 | 40 | 2080000 | 562500 | Actual cost is @7,500 per day
9 | LABOUR | 4 | 13000 | 40 | 2080000 | 280000 | Actual cost is @7,000 per day
10 | LOCAL DIVERS | 4 | 40000 | 20 | 3200000 | 800000
11 | DOPE MAN | 1 | 15000 | 40 | 600000 | 300000 |  | 903.2258
13 | NDT | 2 |  |  | 0
14 | HYDROTESTER | 2 |  |  | 0
15 | CATHODIC PROTECTION TEAM | 3 |  |  | 0
16 | SURVEYORS | 4 |  |  | 0
12 | CAWTHONE CHANNEL 3 COMM PERSONNEL WORKERS | 10 | 5000 | 50 | 2500000 | 2000000
13 | NIGHT P/L SECURITY | 10 | 5000 | 50 | 2500000 | 2000000
13 | CLO (FOR 3 COMMUNITIES) | 3 | 10000 | 50 | 1500000 | 1500000
14 | KRAKRAMA COMMUNITY CHANCE | 5 | 5000 | 50 | 1250000 | 1250000
15 | BILLE COMMUNITY CHANCE | 5 | 5000 | 50 | 1250000 | 1250000
16 | COMMUNITY SKILLED WORKERS SLOT
[5 empty] | 36410000 | 34955000

## Security
Security
| S/N | DESCRIPTION | QTY | DUR (DAY) | UNIT COST | TOTAL COST (NGN) | Actual | PALDOS SCOPE
| 1 | JTF SECURITY SECURITY | 1 | 50 | 320000 | 16000000 | 0 | 16000000
| 2 | CLIENT HSE PR | 1 | 30 | LUMPSUM | L/S | 0 | 500000
| 3 | CLIENT CSR | 1 | 30 | LUMPSUM | 1500000 | 0 | 1500000
| 4 | CLIENT / PRODUCTION CREW PR |  |  |  | 0 | 0 | 0
| 5 | WATER FOR FLUSHING |  |  |  | 300000 | 150000
| 6 | COMPANY WORKERS BOAT | 1 | 31 | 150000 | 4650000 | 0 | 4650000
| 7 | RECHARGE CARD FOR INSPECTORS & Proj. Engr. | 5 | L/S | 20000 | 240000 | 100000
| 8 | FTO SETTLEMENT |  |  |  | 35000000 | 0 | 35000000
| 9 | NIGHT PIPELINE SECURITY | 1 | 31 | 150000 | 4650000
| 10 | WELDERS & FITTERS ASSOCIATION |  |  |  | 5000000 |  | 5000000
| 11 |  | 1 | 31 | 1 | 300000 |  | 300000
[6 empty] | 67640000 | 250000 | 62950000

## Accomodation & Feeding
S/N | DESCRIPTION | QTY | DUR (DAY) | Feeding / (Day) | Accomodation/ (Day) | TOTAL COST (NGN) | Actual
1 | Project Engineer | 1 | 50 | 10000 | 15000 | 1250000 | 962500
2 | CLIENT SUPERVISOR | 1 | 50 | 10000 | 15000 | 1250000 | 962500
3 | CLO | 3 | 50 | 5000 | 0 | 750000 | 750000
4 | QC Officer / Tally Clerk | 1 | 31 | 5000 | 10000 | 465000 | 403000
5 | Site Nurse | 1 | 50 | 5000 | 10000 | 750000 | 650000 | @8k/day
6 | Welders | 2 | 40 | 5000 | 10000 | 1200000 | 520000
7 | Fitters | 1 | 40 | 5000 | 10000 | 600000 | 520000
8 | Operator | 1 | 50 | 5000 | 10000 | 750000 | 650000
9 | Operator Mate | 1 | 50 | 5000 | 10000 | 750000 | 650000
10 | Grinder | 2 | 31 | 5000 | 10000 | 930000 | 403000
11 | Dope Man | 2 | 31 | 5000 | 10000 | 930000 | 403000
12 | Labour/Riggers | 5 | 31 | 5000 | 10000 | 2325000 | 403000
13 | Store man | 1 | 55 | 5000 | 10000 | 825000 | 715000
14 | NDT crew | 1 | 40 | 5000 | 10000 | 600000 | 520000
15 | Pressure testing crew | 2 | 5 | 5000 | 10000 | 150000 | 65000
16 | Survey crew | 4 | 55 | 5000 | 10000 | 3300000 | 715000
17 | CP crew | 3 | 8 | 5000 | 10000 | 360000 | 104000
18 | Tug Boat crew | 3 | 31 | 5000 | 10000 | 1395000 | 0
19 | SPEED BOAT CREW @2 EA | 8 | 60 | 3000 | 0 | 1440000 | 1440000
20 | COMMUNITY WORKERS | 40 | 60 | 3000 | 0 | 7200000 | 7200000
[5 empty] | TOTAL | 27220000 | 18036000
Total No.

## Additonal Community costs
S/N | DESCRIPTION | QTY | DUR (DAY) | Feeding / (Day) | Accomodation/ (Day) | TOTAL COST (NGN) | Actual | Remarks